## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies
Define Project Goals | Jane Doe | 2024-03-01 | 2024-03-15 | Completed | 100% | None
Conduct Stakeholder Analysis | John Smith | <>align="center">2024-03-162024-04-05 | In Progress | 65% | Goal Setting Complete
Develop Action Plans | Lisa Chen | 2024-04-06 | 2024-05-10 | Planned | 0% | Stakeholder Analysis Complete
Set Milestone Review Points | Mike Taylor | 2024-05-11 | 2024-05-31 | Not Started | 0% | Action Plans Approved
Finalize Project Timeline | Sarah Lee | 2024-06-01 | 2024-06-15 | Planned | 0% | Milestone Review Complete