## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Define Project Goals | 2024-03-15 | 2024-03-20 | Jane Smith | Completed | 100%
Conduct Stakeholder Analysis | 2024-03-21 | 2024-03-28 | Mark Johnson | In Progress | 65%
Develop Project Timeline | 2024-03-29 | 2024-04-05 | Lisa Chen | Pending | 0%
Finalize Budget & Resources | 2024-04-06 | 2024-04-12 | Robert Kim | Not Started | 0%
Review & Approve Project Plan | 2024-04-13 | 2024-04-18 | Project Manager | Pending | 0%