## Worksheet
Task / Activity | Owner | Start Date | End Date | Status | Milestones | Dependencies | Resources Required | Risk Assessment | Notes / Remarks
Define Project Vision & Objectives | Project Manager | 2024-04-01 | 2024-04-15 | On Track | Vision Draft Approved, Stakeholder Alignment Completed | - | Team Meeting, Stakeholder Input | Low - Minimal Risk | Initial alignment with leadership team.
Conduct Market & Competitive Analysis | Business Analyst | 2024-04-16 | 2024-05-03 | In Progress | Data Collection Complete, Initial Findings Shared | Vision Approval | Market Research Tools, Data Analyst | Medium - Data Access Delays Possible | Need approval for third-party data access.
Finalize Project Scope & Deliverables | Project Manager & PMO | 2024-05-04 | 2024-05-17 | Not Started | Scope Approval Required | Market Analysis Report | Scope Document, Change Control Board Access | High - Scope Creep Risk | Requires review by Legal and Compliance.
Develop Project Timeline & Work Breakdown Structure (WBS) | Project Manager | 2024-05-18 | 2024-06-10 | Planned | WBS Draft Completed, Gantt Chart Ready | Scope Finalized | Project Management Software, Schedule Expert | Low - Minor Adjustments Expected | Baseline will be shared with stakeholders by June 10.
Stakeholder Engagement Plan & Communication Strategy | Communications Lead | 2024-06-11 | 2024-06-25 | On Track | Schedule Published, Feedback Collected | Timeline & WBS Finalized | Email Templates, Meeting Tools | Low - Minor Adjustments Expected | Bi-weekly syncs scheduled with key stakeholders.
Budget Planning & Resource Allocation | Finance Officer | 2024-06-26 | 2024-07-10 | Not Started | Budget Draft Prepared, Review Pending | Scope & Timeline Finalized | Finance Tools, Vendor Quotes | Medium - Budget Variance Risk | Final budget to be approved by CFO by July 8.
Kickoff Meeting & Team Onboarding | Project Manager | 2024-07-11 | 2024-07-15 | Planned | Team Presentations, Roles Clarified | Budget Approved | Meeting Room, Team Profiles, Onboarding Docs | Low - Attendance Risk | All team members to be present and engaged.