## Worksheet
Task | Owner | Start Date | End Date | Status | Milestone | Priority | Dependencies | Progress (%) | Notes
Define Project Vision & Objectives | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress | Phase 1 Kickoff | High |  | 60% | Align stakeholders on goals and KPIs.
Conduct Market & Competitor Analysis | John Smith | 2024-04-16 | 2024-05-05 | Planned |  | Medium | Vision Definition | 0% | Gather data from 5 key competitors.
Develop Project Timeline & Milestones | Alex Kim | 2024-05-06 | 2024-05-18 | Not Started | Timeline Finalized | High | Market Analysis Complete | 0% | Integrate deliverables into Gantt chart.
Finalize Budget & Resource Plan | Sarah Lee | 2024-05-19 | 2024-06-03 | Planned |  | High | Timeline Approved | 0% | Include contingency and staffing.
Kickoff Team Meeting & Training | Team Lead | 2024-06-04 | 2024-06-07 | Scheduled | Team Onboarded | Medium | Budget Finalized | 0% | Review project charter and roles.