## Worksheet
Task | Owner | Start Date | End Date | Status | Priority
Define Project Goals | Client | 2024-03-15 | 2024-03-18 | In Progress | High
Market Research & Analysis | Freelancer A | 2024-03-19 | 2024-03-25 | Not Started | High
Create Project Timeline & Milestones | Freelancer B | 2024-03-26 | 2024-03-31 | Not Started | Medium
Design Initial Concept | Freelancer C | 2024-04-01 | 2024-04-10 | Not Started | High
Review & Refine Concepts | Client & Freelancer B | 2024-04-11 | 2024-04-15 | Not Started | Medium
Develop Final Version | Freelancer A & C | 2024-04-16 | 2024-05-05 | Not Started | High
Final Delivery & Feedback | Client | 2024-05-06 | 2024-05-12 | Not Started | Low