## Worksheet
Project Name | Goal Statement | Start Date | End Date | Key Milestones | Responsible Party | Status | Progress (%) | Risks & Challenges | Budget (USD)
Global Digital Transformation Initiative | Achieve full digital integration across all business units by Q4 2025. | January 1, 2025 | December 31, 2025 | • Phase 1: System Assessment (Jan–Mar) • Phase 2: Pilot Launch (Apr–Jun) • Phase 3: Full Rollout (Jul–Dec) | IT Leadership Team | On Track | 75% | Data migration complexity, change resistance from staff | $1.8M
Customer Experience Enhancement Program | Increase customer satisfaction score from 78% to 90% within one year. | March 1, 2025 | March 1, 2026 | • Survey Analysis (Mar–Apr) • Process Redesign (May–Jul) • Launch of New Support Portal (Aug–Sep) | Customer Operations Office | In Progress | 50% | Limited budget for UX redesign, staffing delays | $650K
Sustainable Supply Chain Development | Reduce carbon emissions by 30% across supply chain operations by end of 2026. | May 1, 2025 | May 31, 2026 | • Vendor Audits (May–Jun) • Route Optimization (Jul–Sep) • Green Packaging Pilot (Oct–Dec) | Sustainability & Logistics Division | Planning Phase | 15% | Supplier unwillingness to adopt new standards, regulatory uncertainty | $320K