## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Define Project Objectives | 2024-03-01 | 2024-03-15 | Jane Doe (Manager) | Completed | 100%
Conduct Market Research | 2024-03-16 | 2024-04-10 | John Smith (Analyst) | In Progress | 65%
Develop Project Plan | 2024-04-11 | 2024-04-30 | Sarah Lee (Project Lead) | Not Started | 0%
Secure Stakeholder Approval | 2024-05-01 | 2024-05-15 | Mike Chen (Director) | Planned | 0%
Launch Pilot Phase | 2024-05-16 | 2024-06-30 | Team A (Operations) | Not Started | 0%
Total Tasks |  |  | 5 | Average Progress | 48%