## Worksheet
Project Timeline – Goal Setting
Goal Statement | Objective & Purpose
Define clear, measurable, and achievable goals. | Align goals with personal or organizational priorities. | Ensure goals are time-bound and specific. | Involve stakeholders in goal setting process. | Track progress against established benchmarks.
Milestones | Start Date | End Date | Responsible Person | Status
Goal Identified & Approved | 2024-03-15 | 2024-03-18 | Jane Doe | Completed
Initial Action Plan Developed | 2024-03-19 | 2024-03-25 | John Smith | In Progress
Key Performance Indicators Set | 2024-03-26 | 2024-03-31 | Lisa Brown | Pending
First Review Meeting Held | 2024-04-01 | 2024-04-01 | Team Lead | Scheduled
Notes & Reminders
- Review goals quarterly to ensure alignment with evolving objectives. - Adjust timelines as needed based on feedback and performance data. - Celebrate progress milestones to maintain motivation.