## Worksheet
Quarter | Goal | Key Objectives | Milestones | Responsible Party | Deadline | Status
Q1 (Jan–Mar) | Define Project Scope & Objectives | Conduct stakeholder interviews Finalize project charter Identify success metrics | Project charter approved Stakeholder alignment achieved | Project Manager | Mar 31, 2024 | On Track
Q2 (Apr–Jun) | Develop Detailed Plan & Budget | Create work breakdown structure Finalize budget allocation Assign team roles | WBS approved Budget signed off | Team Lead & Finance Officer | Jun 30, 2024 | On Track
Q3 (Jul–Sep) | Execute Project Phases | Complete Phase 1 deliverables Conduct internal reviews Begin user testing | Phase 1 completed User feedback collected | Development Team | Sep 30, 2024 | On Track
Q4 (Oct–Dec) | Deliver & Close Project | Finalize deliverables Conduct client review Document lessons learned | All deliverables approved Closure report submitted | Project Manager & Client Rep | Dec 31, 2024 | Planned