## Worksheet
Project Phase | Goal Statement | Start Date | End Date | Responsible Person | Status | Progress (%)
Phase 1: Planning | Define project scope, objectives, and key stakeholders. | 2024-03-01 | 2024-03-15 | Jane Doe | Completed | 100%
Phase 2: Design | Develop project deliverables and workflow designs. | 2024-03-16 | 2024-04-10 | John Smith | In Progress | 65%
Phase 3: Development | Build core features and conduct internal testing. | 2024-04-11 | 2024-05-30 | Lisa Chen | Planned | 0%
Phase 4: Review & Approval | Final review by stakeholders and obtain sign-off. | 2024-06-01 | 2024-06-15 | Mark Taylor | Not Started | 0%
Phase 5: Launch & Monitor | Deploy project to production and monitor performance. | 2024-06-16 | 2024-09-30 | Emma Rivera | Not Started | 0%