## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Define Project Goals | 2024-03-01 | 2024-03-10 | Jane Smith | Completed | 100%
Conduct Stakeholder Analysis | 2024-03-11 | 2024-03-20 | John Doe | In Progress | 65%
Develop Project Plan | 2024-03-21 | 2024-04-05 | Maria Garcia | Not Started | 0%
Secure Budget Approval | 2024-04-06 | 2024-04-15 | Robert Kim | Pending | 30%
Launch Pilot Phase | 2024-04-16 | 2024-05-10 | Lisa Chen | Not Started | 0%
Template Version – Purpose: Goal Setting ¦ Template Type: Project Timeline