## Worksheet
Project Name | Goal Statement | Target Date | Current Status | Progress (%) | Responsible Person | Priority Level | Key Milestones
Q4 Marketing Campaign | Increase brand awareness by 30% among target demographic by end of Q4. | 2024-12-31 | In Progress | 65% | Sarah Johnson | High | Launch teaser campaign (Oct 1), Social media rollout (Nov 15), Final review (Dec 20)
Product Launch Initiative | Introduce new product line to market within 6 months of approval. | 2025-06-30 | Pending Approval | 15% | Mike Chen | Moderate | Prototype finalization (Jan 30), Beta testing (Mar 15), Market approval (May 20)
Team Expansion Project | Recruit and onboard 5 new team members to support growth initiatives. | 2024-11-30 | On Track | 90% | Lisa Rodriguez | High | Hire process completed (Sep 15), Onboarding started (Oct 5), Training finalized (Nov 10)
Customer Feedback System | Implement a digital feedback platform to capture user insights quarterly. | 2024-10-31 | Delayed | 40% | Jamal Thompson | Moderate | Needs vendor selection (Oct 5), Design approved (Oct 20), Launch scheduled (Nov 15)