## Worksheet
Project Name | Goal Statement | Start Date | Target End Date | Current Progress (%) | Milestones Achieved | Key Responsibilities | Resources Required | Risks & Challenges | Dependencies | Updates / Notes
Launch Mobile App v2.0 | Develop and launch a user-friendly mobile application with enhanced features and improved performance. | 2024-03-15 | 2024-08-31 | 65% | UI/UX Design Complete, Beta Testing Started | Jane Doe (Project Lead), Mark Smith (Dev Team), Sarah Lee (QA) | Design Tools, Cloud Hosting, 5 Devs, QA Team | Delayed API integration; potential bandwidth issues | Server infrastructure approval from IT | Team meeting scheduled for April 10 to review sprint progress.
Expand Market Presence in Europe | Establish a strong brand presence in three European countries through digital marketing and local partnerships. | 2024-04-01 | 2024-11-30 | 30% | Market research completed, brand assets finalized | Alex Johnson (Marketing), Lisa Chen (Partnerships) | Marketing Budget, Local Agency Contracts, Social Media Tools | Cultural differences in messaging; language translation delays | Approval of regional advertising budget from CFO | First campaign launch planned for May 15.
Improve Customer Support System | Implement AI-driven support tools to reduce response time and improve user satisfaction. | 2024-05-01 | 2024-10-31 | 15% | Needs analysis complete, vendor shortlisted | Rahul Patel (Operations), Emily Wong (IT) | AI Platform License, Support Team Training, Cloud Credits | Data privacy compliance risks; integration with legacy system | IT team availability for integration testing | Phase 1 demo scheduled for June 10.