## Worksheet
Project Name | Goal Statement | Start Date | Target End Date | Current Status | Responsible Person | Progress (%) | Key Milestones | Risks & Challenges | Action Items | Next Review Date
Website Redesign | Improve user experience and increase engagement by 30% within six months. | 2024-03-01 | 2024-09-30 | In Progress | Sarah Johnson | 65% | UI/UX Finalization, Content Audit, Launch Preparation | Limited design team availability during Q3 | Finalize feedback from beta testers | 2024-06-15
Customer Onboarding System | Reduce onboarding time from 5 days to under 3 days by Q4. | 2024-04-01 | 2024-12-31 | Planning Phase | David Kim | 20% | Requirement Gathering, Process Mapping, Tool Selection | Potential integration issues with existing CRM | Conduct user interviews in Q2 | 2024-05-30
Marketing Campaign Launch | Increase brand awareness by 40% among target demographics in Q3. | 2024-05-01 | 2024-08-31 | Scheduled | Lisa Chen | 50% | Pre-campaign planning, ad creative approval, social media rollout | Budget constraints and platform algorithm changes | Finalize ad copy and schedule | 2024-07-05