## Worksheet
Project Name | Goal Statement | Target Date | Status | Progress (%) | Owner (Manager) | Key Milestones | Risk & Challenges
Q4 Marketing Campaign | Increase brand awareness by 30% in Q4 through targeted digital ads and influencer partnerships. | December 31, 2024 | On Track | 75% | Sarah Johnson | Launch teaser content (Oct), Influencer rollout (Nov), Final reporting (Dec) | Budget overruns in early phase; content creation delays
Product Launch - Alpha Version | Successfully launch the first version of the new product with core features by end of Q3. | September 30, 2024 | Delayed | 45% | Michael Chen | UI/UX finalization (Aug), Beta testing (Sep), Release planning (Oct) | Technical bugs discovered during testing; team bandwidth issues
Customer Retention Initiative | Improve customer retention rate by 25% through personalized email campaigns and loyalty rewards. | March 31, 2025 | Planned | 0% | Lisa Wong | Data analysis (Jan), Campaign design (Feb), Pilot launch (Mar) | Need access to CRM data for full segmentation