## Worksheet
Quarter | Project Name | Goal Statement | Target Date | Status | Responsible Person | Progress (%) | Notes
Q1 2024 | Product Launch Initiative | Launch a new product line by March 31, 2024. | March 31, 2024 | On Track | John Smith | 85% | Prototype testing completed. Marketing materials in final review.
Q1 2024 | Customer Retention Program | Improve customer retention rate by 15% by April 30, 2024. | April 30, 2024 | In Progress | Sarah Lee | 40% | Initial survey launched. Feedback analysis pending.
Q2 2024 | Team Expansion Planning | Recruit and onboard 5 new team members by June 30, 2024.June 30, 2024 | Pending Approval | David Chen | 10% | HR team reviewing requirements. Budget approval pending.
Q2 2024 | Digital Transformation Workshop | Conduct training for all employees on new digital tools by May 31, 2024. | May 31, 2024 | Delayed | Lisa Wong | 0% | Equipment delivery delayed. Revised date to July 15, 2024.
Q3 2024 | Revenue Growth Strategy | Increase Q3 revenue by 20% through new markets. | September 30, 2024 | Not Started | Michael Reed | 0% | Market research phase underway. Initial findings due August 15.