## Worksheet
Week | Goal | Target Date | Progress (%) | Status | Notes
Week 1 | Complete project proposal | 2023-10-08 | 40% | In Progress | Needs feedback from team lead.
Week 2 | Finalize budget plan | 2023-10-15 | 10% | Pending | Waiting for financial data.
Week 3 | Conduct stakeholder meeting | 2023-10-22 | 0% | Not Started | Schedule confirmed for next Monday.
Week 4 | Submit final report | 2023-10-29 | 0% | Not Started | Depends on Week 3 outcomes.
Week 5 | Review and present findings | 2023-11-05 | 0% | Not Started | Prepare presentation deck.