## Worksheet
Growth Planning Business Plan Template (Team Use)
Section | Objective | Action Items | Responsible Team Member(s) | Deadline | Status
1. Market Analysis & Opportunity Assessment
Market Research Summary | Define target market size and growth trends. | Collect industry reports, customer surveys, and competitor data. | Jane Doe (Marketing) | 2024-07-15 | Pending
Competitor Benchmarking | Identify top 5 competitors and analyze their strengths/weaknesses. | Create a comparative matrix with key performance indicators. | Mike Chen (Strategy) | 2024-07-20 | In Progress
2. Strategic Goals & KPIs
SMART Goal Definition (Q3 2024) | Establish measurable, time-bound goals for revenue and customer growth. | Develop 3 SMART goals aligned with business vision. | Sarah Williams (Leadership) | 2024-07-10 | Completed
KPI Dashboard Setup | Create a live tracking dashboard for all key performance metrics. | Configure Google Sheets/Excel with automated formulas and charts. | Tom Parker (Data Analytics) | 2024-07-31 | Pending
3. Growth Strategy & Execution Plan
Product Expansion Roadmap | Outline new features or product lines for customer acquisition. | Define release dates, resource needs, and success criteria. | Lisa Tran (Product) | 2024-08-15 | In Progress
Marketing Campaign Plan | Develop a multi-channel campaign to increase brand visibility. | Create content calendar, budget allocation, and channel strategy. | Jane Doe (Marketing) | 2024-08-10 | In Progress
4. Team Roles & Accountability Matrix
Ownership Assignment Grid | Clarify decision-making authority and accountability. | Map out RACI (Responsible, Accountable, Consulted, Informed) model. | Sarah Williams (Leadership) | 2024-07-18 | Pending
5. Review Cycle & Feedback Process
Bi-Weekly Check-In Schedule | Ensure alignment and timely progress updates. | Set recurring team meetings every Monday at 10:00 AM. | All Team Leads | Ongoing | In Progress
Summary: Overall Growth Plan Status (as of 2024-07-08)
Total Actions Completed: 1 / 9 Key Dependencies Remaining: Market data access, leadership sign-off. |  |  | Next Review Date: August 12, 2024
This document is designed for internal team use. Update regularly and share with stakeholders.