## Worksheet
Month | Key Objective | Target Metric (KPI) | Current Status | Progress (%) | Action Plan | Status Update
January 2024 | Growth Strategy Initiation | Customer Acquisition: +15% | 10% | 66.7% | Launch digital ad campaign, expand social media outreach | In progress – initial data shows 8% increase in leads
February 2024 | Customer Retention Enhancement | Retention Rate: 85% | 79% | 92.9% | Implement loyalty rewards, improve onboarding process | Pilot program launched; feedback positive from first 300 users
March 2024 | Product Feature Expansion | New Features Launch: 3 major updates | 1 feature completed | 33.3% | Fully develop and test remaining features; user testing scheduled | On track – development team ahead of schedule on two features
April 2024 | Digital Marketing Optimization | CTR: 5% | 3.8% | 76.0% | Re-optimize ad copy and targeting, A/B testing ongoing | A/B tests show improved performance on two variants
May 2024 | Revenue Growth Target | Monthly Revenue: $150K+ | $125K | 83.3% | Increase upselling, enhance sales team training | Sales pipeline increasing; forecast for month-end shows potential to exceed target
Average Progress |  |  |  | 73.9%