## Worksheet
Growth Planning Dashboard
Strategic Growth Plan - Q3 2024
Initiative | Objective | Target Metric | Current Status | Target Date | Action Owner
New Market Expansion - APAC Region | Enter two new markets (India, Singapore) with localized product offering | 10% market penetration by Dec 2024 | In Progress - Market research complete, partner agreements pending | Dec 31, 2024 | Sarah Kim (Global Expansion Lead)
Product Line Enhancement | Launch two new product features to increase customer retention by 15% | Feature adoption rate of 40% within Q4 | In Development - UI/UX testing in progress | Nov 15, 2024 | James Chen (Product Manager)
Customer Acquisition Campaign | Increase qualified leads by 30% through digital marketing strategy | 2,000 new leads by end of quarter | Active - Campaigns live, early results positive | Oct 31, 2024 | Lisa Wong (Marketing Director)
Digital Transformation Initiative | Implement CRM automation to reduce customer onboarding time by 50% | Onboarding time reduced from 7 days to under 3.5 days | Pilot phase complete, full rollout scheduled | Oct 10, 2024 | David Patel (IT Operations)
Talent Development Program | Launch leadership training program to improve team retention and performance | 90% employee participation in Q3 programs | Planning phase - curriculum being developed | Sep 30, 2024 | Maria Lopez (HR Director)
Total Initiatives: |  |  |  |  | 5
Notes:
All targets are reviewed monthly by the Executive Planning Committee.
Status updates required every Friday for tracking.
Progress metrics updated in real-time via company dashboard (link: https://dashboard.company.com/growth).