## Worksheet
Growth Planning - Advanced Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
T001 | Market Research & Analysis | 2025-04-01 | 2025-04-15 | 15 | Ongoing
Product Development Phase 1 | Prototype Design | 2025-04-16 | 2025-05-31 | 46 | Ongoing
T003 | User Testing & Feedback Integration | 2025-06-01 | 2025-06-30 | 30 | Delayed
T004 | Go-to-Market Strategy | 2025-07-01 | 2025-07-15 | 15 | Completed
T005 | Launch Campaign Execution | 2025-07-16 | 2025-08-31 | 47 | Ongoing
T006 | Performance Monitoring & Optimization | 2025-09-01 | 2025-11-30 | 91 | Completed