## Growth Planning - Gantt Chart
Growth Planning - Gantt Chart (Basic Style)
Task ID | Task Name | Start Date | End Date | Status | % Complete
001 | Market Research Phase | 2025-04-01 | 2025-04-15 | In Progress | 75%
002 | Product Development | 2025-04-16 | 2025-06-30 | In Progress | 45%
003 | User Testing & Feedback | 2025-07-01 | 2025-07-15 | Not Started | 0%
004 | Launch Preparation | 2025-07-16 | 2025-07-31 | Not Started | 0%
005 | Full Market Launch | 2025-08-01 | 2025-08-15 | Not Started | 0%
006 | Growth Analytics & Optimization | 2025-08-16 | 2025-10-31 | Not Started | 0%
007 | Q4 Review & Planning | 2025-11-01 | 2025-11-30 | Not Started | 0%
008 | Budget & Resource Allocation Review | 2025-12-01 | 2025-12-15 | Not Started | 0%
009 | Annual Growth Plan Finalization | 2025-12-16 | 2025-12-31 | Not Started | 0%
010 | Year-End Report & Presentation | 2025-12-31 | 2025-12-31 | Not Started | 0%
Gantt Chart Timeline (Visual)