## Worksheet
Growth Planning Gantt Chart (Business Use)
Task/Phase | Start Date | End Date | Duration (Days) | Status
Market Research & Analysis | 2024-01-15 | 2024-03-31 | 75 | Completed
Strategic Planning & Goal Setting | 2024-04-01 | 2024-05-15 | 45 | In Progress
Product Development & MVP Build | 2024-05-16 | 2024-08-31 | 108 | In Progress
Marketing & Launch Campaigns | 2024-09-01 | 2024-11-30 | 91 | Pending
User Acquisition & Onboarding | 2024-12-01 | 2025-03-31 | 121 | Pending
Growth Optimization & Scaling | 2025-04-01 | 2025-12-31 | 306 | Pending
Milestone: MVP Release (Version 1.0) | 2024-08-31 | 2024-08-31 | 1 | Completed
Milestone: Market Launch (Q4 2024) | 2024-11-30 | 2024-11-30 | 1 | Pending
Total Duration: | 2024-01-15 to 2025-12-31 (743 Days) |  | 743 | Planning Phase
Note:This Gantt chart represents a high-level business growth plan. Actual timelines may vary based on resource availability and market conditions.