## Worksheet
Growth Planning - Client View Gantt Chart
Quarterly Strategic Initiative Timeline (Q2 2024)
Project Phase | Objective | Start Date | End Date | Status | Progress
Phase 1: Market Research | Analyze customer needs and competitor landscape | 2024-04-01 | 2024-05-15 | In Progress
Phase 2: Product Development | Design and prototype new product features | 2024-05-16 | 2024-07-31 | In Progress
Phase 3: Beta Testing | Conduct user testing with pilot group | 2024-08-01 | 2024-09-15 | Delayed
Phase 4: Launch Preparation | Finalize go-to-market strategy and marketing assets | 2024-09-16 | 2024-10-31 | Completed
Phase 5: Full Rollout | Launch product to all target markets | 2024-11-01 | 2024-12-31 | Not Started
Note:This Gantt chart provides a high-level view of the Growth Planning timeline for client review. Actual timelines may vary based on stakeholder feedback and market conditions.