## Worksheet
Growth Planning Gantt Chart - Dashboard View
Phase / Task | Start Date | End Date | Duration (Days) | Status | Progress
Market Research & Analysis | 2024-04-01 | 2024-04-15 | 15 | In Progress
Goal Setting & KPIs Definition | 2024-04-16 | 2024-05-15 | 30 | In Progress
Product Development Sprint 1 | 2024-05-16 | 2024-06-30 | 45 | In Progress
Marketing Campaign Launch (Phase 1) | 2024-07-01 | 2024-07-31 | 31 | Completed
User Feedback & Iteration Cycle | 2024-08-01 | 2024-08-31 | 31 | Delayed
Scale to New Markets (Q3) | 2024-09-01 | 2024-11-30 | 91 | In Progress
Performance Review & Planning (Q4) | 2024-12-01 | 2024-12-31 | 31 | In Progress