## Worksheet
Growth Planning - Gantt Chart (Data Version)
Task ID | Task Name | Start Date | End Date | Status | Jan-2024 | Feb-2024 | Mar-2024 | Apr-2024 | May-2024 | Jun-2024
T001 | Market Research Phase 1 | 2024-01-05 | 2024-02-15 | In Progress | █ | █
T002 | Product Development MVP | 2024-01-15 | 2024-04-30 | In Progress | █ | █ | █ | █
T003 | User Testing & Feedback Loop | 2024-03-15 | 2024-05-15 | Not Started |  |  | █ | █ | █
T004 | Go-to-Market Strategy Finalization | 2024-05-01 | 2024-06-15 | Not Started |  |  |  |  | █ | █
T005 | Full Launch & Monitoring | 2024-06-16 | 2024-07-31 | Pending Launch
Overall Project Progress |  |  |  |  | ████░░░░ (40% complete)
Note: Gantt cells represent task timeline coverage. █ = active phase, blank = no activity. Data Version – For planning and tracking purposes only.