## Worksheet
Growth Planning - Detailed Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
GP-001 | Market Research & Analysis | 2025-04-01 | 2025-04-15 | 15 | In Progress
GP-002 | Define Target Audience Segmentation | 2025-04-16 | 2025-04-30 | 15 | In Progress
GP-003 | Develop Product Positioning Strategy | 2025-05-01 | 2025-05-14 | 14 | Not Started
GP-004 | Create Marketing Campaign Framework | 2025-05-15 | 2025-06-14 | 31 | Not Started
M-01 | Q2 Growth Planning Approval | 2025-06-15 | 2025-06-15 | 1 | Milestone Reached
GP-005 | Develop Sales Enablement Materials | 2025-06-16 | 2025-07-14 | 30 | Not Started
GP-006 | Implement Digital Lead Generation Strategy | 2025-07-15 | 2025-08-31 | 48 | Not Started
GP-007 | Customer Onboarding Process Design | 2025-09-01 | 2025-10-14 | 45 | Not Started
GP-008 | Q3 Growth Review & Adjustments | 2025-10-15 | 2025-10-31 | 17 | Not Started
M-02 | Q3 Growth Execution Launch | 2025-11-01 | 2025-11-01 | 1 | Milestone Reached
GP-009 | Expand to New Market Region | 2025-11-02 | 2026-03-31 | 150 | Not Started
GP-010 | Annual Growth Plan Review & Forecast Update | 2026-04-01 | 2026-04-30 | 30 | Not Started
This Gantt chart template provides a detailed view of the Growth Planning roadmap with task timelines, progress tracking, and key milestones.