## Worksheet
Growth Planning - Financial View Gantt Chart
Task ID | Project Phase / Activity | Start Date | End Date | Budget (USD) | Actual Spend (USD) | % Complete
P1 | Market Research & Competitive Analysis | 2024-01-05 | 2024-03-15 | $85,000 | $78,456 | 92.3%
P2 | Product Development & Prototyping | 2024-01-15 | 2024-07-30 | $650,000 | $498,367 | 76.7%
P3 | Marketing & Go-to-Market Strategy | 2024-04-01 | 2024-10-31 | $350,000 | $167,895 | 48.0%
P4 | Sales Training & Channel Partner Onboarding | 2024-06-15 | 2024-11-30 | $185,000 | $97,345 | 52.6%
P5 | Product Launch & Early Customer Acquisition | 2024-08-01 | 2025-01-31 | $765,000 | $349,678 | 45.7%
P6 | Performance Analysis & Revenue Optimization | 2025-01-01 | 2025-06-30 | $485,000 | $98,765 | 20.4%
Total Project |  |  |  | $2,520,000 | $1,391,506 | 55.2%