## Worksheet
Growth Planning - Large Business Gantt Chart
Task ID | Project Phase | Task Name | Start Date | End Date | Status | Progress (%)
PH-01 | Phase 1: Market Research & Analysis | Initiating Growth Strategy
1.1 | Market Analysis | Competitor Benchmarking & SWOT Review | 2025-04-01 | 2025-04-15 | In Progress
1.2 | Market Segmentation | Customer Persona Development & Targeting Strategy | 2025-04-16 | 2025-04-30 | In Progress
1.3 | Data Collection & Validation | Primary Research (Surveys, Focus Groups) | 2025-05-01 | 2025-05-14 | Not Started
PH-02 | Phase 2: Product Development & Roadmap | Product Innovation Cycle
2.1 | Concept Design | Feature Prioritization & MVP Specification | 2025-05-15 | 2025-06-10 | Not Started
2.2 | Prototype Development | UI/UX Design & Technical Prototype Build | 2025-06-11 | 2025-07-31 | Not Started
🎯 MILESTONE: Product Prototype Finalized (July 31, 2025)
PH-03 | Phase 3: Go-To-Market Strategy | Launch Preparation
3.1 | Pricing & Packaging | Value-based Pricing Model & Tiered Offerings | 2025-08-01 | 2025-08-15 | Not Started
3.2 | Marketing Campaign Design | Content Strategy, Launch Events & Digital Ads | 2025-08-16 | 2025-09-14 | Not Started
🚀 MILESTONE: Official Product Launch (September 15, 2025)
PH-04 | Phase 4: Post-Launch Growth | Scaling & Optimization
4.1 | Customer Acquisition | Campaign Analytics & ROI Optimization (First 3 Months) | 2025-09-16 | 2025-12-31 | Not Started
4.2 | Growth Monitoring & KPIs | Monthly Performance Dashboards & Feedback Loops | 2025-10-01 | 2026-12-31 | Not Started
🔥 MILESTONE: Q1 2026 – Achieve 50,000 Active Users