## Worksheet
Growth Planning - Manager View Gantt Chart
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%)
Phase 1: Strategy & Planning
STR-101 | Market Research Analysis | Jane Smith | 2024-06-03 | 2024-07-15 | In Progress | 68%
Phase 2: Product Development
DEV-201 | Feature Design & Wireframing | Mike Chen | 2024-07-16 | 2024-08-30 | In Progress55%
Phase 3: Testing & Validation
TEST-301 | User Acceptance Testing (UAT) | Sarah Johnson | 2024-09-0145%45%
Phase 4: Launch & Growth
LAUNCH-401 | Product Launch Campaign | Liam Brown35%35%
MS-001 | Milestone: Strategy Finalized | Project Lead100%100%
MS-002 | Milestone: MVP Ready for Testing | Product Manager100%100%
MS-003 | Milestone: Official Product Launch | Marketing Director100%100%