## Worksheet
Growth Planning - Gantt Chart (Office Use)
Task | Start Date | End Date | Duration (days) | Progress | Responsible Team
Market Research Phase | 2024-07-01 | 2024-07-15 | 15 | 67% | Marketing Team
Product Feature Development | 2024-07-10 | 2024-08-31 | 53 | 85% | Product Team
Campaign Design & Approval | 2024-07-20 | 2024-08-15 | 36 | 91% | Marketing Team
User Testing & Feedback Collection | 2024-08-16 | 2024-08-31 | 16 | 35% | UX Team
Final Product Launch | 2024-09-01 | 2024-09-30 | 31 | 5% | Executive Team
Milestone: Project Kickoff | 2024-07-01 | 2024-07-01 | 1 | 100% | Project Manager
Milestone: Feature Freeze | 2024-08-31 | 2024-08-31 | 1 | 100% | Product Manager
Milestone: Launch Day | 2024-09-30 | 2024-09-30 | 1 | 5% | CEO Office
Core Infrastructure Upgrade | 2024-07-15 | 2024-08-31 | 47 | 95% | IT Department