## Growth Planning - Gantt Chart
Growth Planning - Gantt Chart (One Page)
Task | Start Date | End Date | Duration (Days) | Status
Market Research & Analysis | 2024-01-05 | 2024-01-31 | 27
Define Target Audience | 2024-01-15 | 2024-01-31 | 17
Develop Product Strategy | 2024-02-01 | 2024-03-15 | 43
Prototype Development | 2024-03-16 | 2024-05-15 | 60
User Testing & Feedback | 2024-05-16 | 2024-06-30 | 46
Finalize Product Launch Plan | 2024-07-01 | 2024-07-31 | 31
Product Launch | 2024-08-01 | 2024-08-01 | -
Post-Launch Monitoring | 2024-08-02 | 2024-11-30 | 121
Quarterly Review & Optimization | 2024-11-01 | 2024-11-30 | 30
Plan Next Growth Cycle | 2024-12-01 | 2024-12-31 | 31
Annual Growth Report | 2024-12-15 | 2024-12-31 | 17