## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
Phase 1: Strategy Development | 2025-04-01 | 2025-04-30 | 30 | In Progress
Market Research & Analysis | 2025-04-01 | 2025-04-15 | 15 | In Progress
Competitor Benchmarking | 2025-04-10 | 2025-04-25 | 16 | In Progress
Define Growth Goals | 2025-04-20 | 2025-04-30 | 11 | Pending
Phase 2: Product Planning | 2025-05-01 | 2025-06-30 | 61 | Pending
Feature Prioritization | 2025-05-01 | 2025-05-15 | 14 | Pending
Prototype Design | 2025-05-16 | 2025-06-15 | 31 | Pending
User Feedback Loop | 2025-06-16 | 2025-06-30 | 15 | Pending
Phase 3: Launch & Scale | 2025-07-01 | 2025-12-31 | 184 | Pending
Alpha Launch (Internal) | 2025-07-01 | 2025-07-31 | 31 | Pending
Beta Launch (External) | 2025-08-15 | 2025-10-31 | 77 | Pending
Full Market Rollout | 2025-11-01 | 2025-12-31 | 61 | Pending
Key Milestone: Q3 Growth Target | 2025-09-30 | 2025-09-30 | - | Milestone Achieved
Growth Planning Gantt Chart (Planning View) - Data as of May 5, 2025