## Worksheet
Growth Planning - Professional Gantt Chart
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
G1 | Market Research & Analysis | 2024-01-05 | 2024-01-31 | Active
G2 | Define Target Customer Segments | 2024-01-15 | 2024-01-31 | Active
G3 | Develop Product Strategy | 2024-02-01 | 2024-03-15 | In Progress
G4 | Design MVP Prototype | 2024-02-15 | 2024-03-31 | In Progress
G5 | Conduct User Testing Phase 1 | 2024-04-01 | 2024-04-30 | Not Started
G6 | Refine Product Based on Feedback | 2024-05-01 | 2024-05-31 | Not Started
G7 | Prepare Go-to-Market Strategy | 2024-06-01 | 2024-06-30 | Not Started
G8 | Launch Product & Campaign | 2024-07-01 | 2024-07-31 | Not Started