## Worksheet
Growth Planning - Gantt Chart Report Version
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
Phase 1: Market Research & Analysis
MR-01 | Industry Trend Analysis | 2024-03-01 | 2024-03-15 | 15 | Pending
MR-02 | Competitor Benchmarking | 2024-03-16 | 2024-03-31 | 16 | In Progress
Phase 2: Strategy Development
SD-01 | Target Audience Segmentation | 2024-04-01 | 2024-04-15 | 15 | Pending
SD-02 | Growth Strategy Blueprint | 2024-04-16 | 2024-05-15 | 30 | Pending
Phase 3: Execution Planning
EP-01 | Resource Allocation Plan | 2024-05-16 | 2024-05-31 | 16 | Pending
EP-02 | Timeline & Milestone Setup | 2024-06-01 | 2024-06-30 | 30 | Pending
M-01 | Strategy Approval | 2024-06-30 | 2024-06-30 | 1 | Milestone Achieved
Phase 4: Implementation & Monitoring
IM-01 | Product Launch Campaign | 2024-07-01 | 2024-07-31 | 31 | Pending
IM-02 | Performance Tracking & KPIs | 2024-08-01 | 2024-11-30 | 123 | Pending
M-02 | Quarterly Growth Review | 2024-11-30 | 2024-11-30 | 1 | Pending
Total Duration: |  |  |  | 239 days
Report Version ¦ Generated on:¦ Growth Planning Timeline (Q1-Q4 2024)