## Growth Planning - Gantt Chart
Growth Planning - Gantt Chart (Simple)
Task | Start Date | End Date | Duration (Days) | Status
Market Research | 2024-01-01 | 2024-01-15 | 15 | In Progress
Product Development Phase 1 | 2024-01-16 | 2024-03-31 | 75 | Not Started
User Testing & Feedback Collection | 2024-04-01 | 2024-05-15 | 45 | Not Started
Go-to-Market Strategy Finalization | 2024-05-16 | 2024-06-30 | 45 | Not Started
Limited Beta Launch | 2024-07-01 | 2024-08-31 | 61 | Not Started
Full Product Launch | 2024-09-01 | 2024-12-31 | 121 | Not Started