## Worksheet
Growth Planning - Gantt Chart (Small Business)
Task | Start Date | End Date | Status | Progress
Phase 1: Market Research | 2024-01-05 | 2024-01-31 | In Progress
• Conduct competitor analysis | 2024-01-05 | 2024-01-15 | Completed
• Survey target customers | 2024-01-16 | 2024-01-31 | In Progress
Phase 2: Product Development | 2024-02-01 | 2024-03-31 | In Progress
• Design prototype | 2024-02-01 | 2024-03-15 | In Progress
• Test user feedback loop | 2024-03-16 | 2024-03-31 | Pending
Phase 3: Marketing Strategy | 2024-04-01 | 2024-05-15 | Scheduled
• Develop brand messaging | 2024-04-01 | 2024-04-15 | Scheduled
• Launch social media campaigns | 2024-04-16 | 2024-05-15 | Scheduled
Milestone: Product Launch (v1.0) | 2024-05-31 | 2024-05-31 | Pending
Phase 4: Sales & Distribution | 2024-06-01 | 2024-08-31 | Scheduled
• Onboard first retail partners | 2024-06-01 | 2024-07-15 | Scheduled
• Begin direct online sales | 2024-07-16 | 2024-08-31 | Scheduled
Milestone: First Quarter Revenue Goal Achieved | 2024-08-31 | 2024-08-31 | Pending
Note:This Gantt Chart outlines a small business growth plan across four key phases. Progress bars reflect estimated completion percentages.