## Worksheet
Growth Planning - Gantt Chart (Team Use)
Task ID | Task Name | Owner | Start Date | Due Date | Status | % Complete
Phase 1: Market Research & Analysis
MR-01 | Conduct Competitive Analysis | Alice Johnson | 2024-04-01 | 2024-04-15 | In Progress
MR-02 | Customer Persona Development | James Reed | 2024-04-10 | 2024-05-10 | In Progress
Phase 2: Growth Strategy & Planning
GS-01 | Define KPIs and OKRs | Sarah Williams | 2024-05-01 | 2024-05-15 | In Progress
GS-02 | Draft Growth Framework | David Kim | 2024-05-15 | 2024-06-15 | In Progress
Phase 3: Implementation & Launch
EX-01 | Build Marketing Campaign | Emily Chen | 2024-06-01 | 2024-07-31 | In Progress
M-01 | Q3 Launch Event | Team Lead | 2024-07-25 | 2024-07-25 | Completed | 100%
Phase 4: Performance Tracking & Optimization
MO-01 | Monthly Review Meetings | Lisa Patel | 2024-08-01 | Ongoing | In Progress | 10%