## Worksheet
Growth Planning - Gantt Chart Template
Template Type:Gantt Chart
Style/Version:Template Version 1.0
Purpose:Growth Planning
Task | Start Date | End Date | Duration (days) | Progress
Market Research & Analysis | 2024-04-01 | 2024-04-15 | 15 | 85%
Product Development Phase 1 | 2024-04-16 | 2024-05-31 | 46 | 75%
User Testing & Feedback | 2024-06-01 | 2024-06-15 | 15 | 95%
Marketing Strategy Development | 2024-06-16 | 2024-07-15 | 30 | 65%
Launch Campaign Execution | 2024-07-16 | 2024-08-31 | 47 | 35%
Product Launch (Milestone) | 2024-09-01 | 2024-09-01 | -
Post-Launch Monitoring | 2024-09-02 | 2024-11-30 | 91 | 5%
Iterative Improvements | 2024-12-01 | 2025-03-31 | 122 | 5%
Total Duration | 268 days (approx. 9 months)
Note: This Gantt Chart Template is designed for Growth Planning purposes and can be customized based on project specifics.