## Worksheet
Growth Planning - Home Template (Extended)
Quarter | Key Objective | Target Metric | Current Level | Growth Target (%) | Baseline (Q1) | Growth Rate (QoQ) | Action Plan | Owner | Status | Progress (%) | Notes / Risks
Q1 2024 | Sales Expansion in North Region | Revenue ($) | $1,200,000 | +15% | $1,250,000 | -4% | Launch new marketing campaign & expand sales team | John Doe | On Hold | 75% | Delayed by vendor onboarding.
Q2 2024 | Product Launch - New Feature Suite | User Adoption Rate (%) | 35% | +10% | 38% | -3% | Conduct beta testing and UX optimization | Jane Smith | In Progress | 60% | Early feedback positive.
Q3 2024 | Customer Retention Improvement | Retention Rate (%) | 85% | +5% | 87% | -2% | Introduce loyalty program & personalization engine | Alice Brown | On Hold | 45% | Budget approval pending.
Q4 2024 | Market Expansion - Southeast Asia | Monthly Active Users (MAU) | 15,000 | +35% | 18,693 | -2% | Partner with local distributors & localize content | Mike Johnson | At Risk | 25% | Regulatory hurdles in country X.
Total Growth Target: |  |  |  | +10.5% | - | - | - | - | Avg. Progress: 56% | 82% (Target: 90%)
Legend & Status Indicators
Color Code: ✅ In Progress (Green) ⚠️ On Hold (Orange) ❌ At Risk (Red) | [5 empty] | Progress Scale: 0–25% = Low 26–50% = Moderate 51–75% = Good 76–100% = Excellent