## Worksheet
Growth Planning - Team Use Template
Phase | Objective | Key Metrics | Target Date | Status | Owner(s) | Action Items
Phase 1: Assessment | Understand current growth status and identify key areas for improvement | Customer acquisition cost, retention rate, CAC:LTV ratio | 2024-06-30 | In Progress | Jane Doe (Product), Mark Lee (Marketing) | Conduct customer survey, analyze CRM data, review past campaigns
Phase 2: Strategy Development | Create a comprehensive growth strategy based on insights from Phase 1 | Strategic roadmap clarity, stakeholder alignment score | 2024-07-15 | To Do | Team Lead (All Departments) | Host strategy workshop, draft initial growth plan
Phase 3: Implementation Planning | Break down strategy into actionable tasks and assign responsibilities | Task completion rate, resource allocation accuracy | 2024-07-31 | To Do | All Team Leads | Create detailed project plan with timelines and dependencies
Phase 4: Execution & Monitoring | Launch initiatives and monitor progress weekly | Daily active users, conversion rate, engagement metrics | Ongoing (2024-08-15 to 2025-03-31) | To Do | Project Managers (All Teams) | Implement A/B tests, track KPIs weekly, report progress
Phase 5: Review & Optimization | Analyze results and refine strategies for next cycle | ROI on initiatives, improvement in KPIs vs. baseline | 2025-04-15 | To Do | Executive Team & Cross-functional Leads | Hold retrospective meeting, document lessons learned, update plan
Summary of Key Growth Goals for Q3 2024 - Q1 2025
Note: This template is designed for team collaboration and regular updates. Update progress weekly and ensure all team members are aligned with current priorities.