## Worksheet
Date | Task Description | Assigned To | Status | Due Date | Remarks
01/05/2024 | Review quarterly growth metrics and adjust KPIs | Jane Smith | In Progress | 08/05/2024 | Needs input from marketing team.
15/05/2024 | Conduct client feedback session for new product features | Mike Johnson | Pending | 22/05/2024 | Schedule meeting with 5 key clients.
30/05/2024 | Update onboarding process for new growth initiatives | Sarah Lee | Completed | 30/05/2024 | All stakeholders approved.
10/06/2024 | Develop training materials for growth strategy rollout | David Brown | Not Started | 17/06/2024 | Waiting on finalized plan from leadership.
25/06/2024 | Review and approve Q3 growth roadmap | Emily Davis | Pending | 01/07/2024 | Awaiting final budget alignment.
Total Tasks: 5 ¦ Completed: 1 ¦ In Progress: 1 ¦ Pending: 2 ¦ Not Started: 1