## Worksheet
Task ID | Task Description | Owner | Start Date | End Date | Status | Progress (%) | Prioritization (1-5)
GP-001 | Market Research & Competitor Analysis | Jane Smith | 2023-10-05 | 2023-11-15 | In Progress |  | 5
GP-002 | Define Target Customer Segments | Mike Johnson | 2023-11-16 | 2023-11-30 | Pending |  | 5
GP-003 | Develop Growth Strategy Framework | Sarah Lee | 2023-11-05 | 2024-01-15 | In Progress |  | 5
GP-004 | Identify Key Growth Channels (Digital & Physical) | Alex Turner | 2023-11-20 | 2024-01-31 | Pending |  | 4
GP-005 | Design Customer Acquisition Campaigns | Lisa Wang | 2024-01-16 | 2024-03-15 | Pending |  | 4
GP-006 | Conduct A/B Testing for Marketing Tactics | Raj Patel | 2024-03-15 | 2024-05-15 | Pending |  | 3
GP-007 | Implement & Monitor Growth Initiatives | Diana Cruz | 2024-05-16 | 2024-11-30 | Pending |  | 5
GP-008 | Review & Optimize Growth Metrics (KPIs) | Taylor Reed | 2024-10-15 | 2024-11-30 | Pending |  | 4
This Growth Planning Project Plan is designed for Advanced tracking and reporting. Last updated on October 5, 2023.