## Worksheet
GROWTH PLANNING - PROJECT PLAN - ANALYSIS VIEW
Phase | Objective | Key Activities | Responsible Team | Scheduled Start | Scheduled End | Status | KPI / Outcome Measure
PHASE 1: STRATEGIC ASSESSMENT & MARKET ANALYSIS
Phase 1A | Define Growth Goals and Targets | Conduct SWOT analysis, market opportunity assessment, financial modeling | Strategy & Planning Team | 2023-10-01 | 2023-10-15 | In Progress | Clear growth objectives defined (95% completion)
Phase 1B | Market Segmentation & Customer Profiling | Customer surveys, data clustering, persona development | Data Analytics & Marketing | 2023-10-16 | 2023-10-31 | Not Started | Three distinct customer segments identified and documented
PHASE 2: PRODUCT & SERVICE STRATEGY DEVELOPMENT
Phase 2A | Product Innovation Roadmap Creation | Brainstorming sessions, concept validation testing | R&D and Product Management | 2023-11-01 | 2023-11-30 | Not Started | Minimum Viable Product (MVP) concept approved by leadership
Phase 2B | Service Enhancement Planning | Evaluate service touchpoints, redesign customer journey map | Customer Experience Team | 2023-11-01 | 2023-11-30 | Not Started | CX score improvement target set (from 78 to 85)
PHASE 3: MARKETING & SALES STRATEGY IMPLEMENTATION
Phase 3A | Go-to-Market Campaign Launch | Create digital and traditional marketing assets, launch campaigns | Marketing & Sales Team | 2023-12-01 | 2024-01-15 | Not Started | Campaign reach: 5M+ impressions; conversion rate increase by 8%
Phase 3B | Sales Enablement & Channel Development | Train salesforce, partner integration, channel agreements | Sales Operations & Partnerships | 2023-12-01 | 2024-01-31 | Not Started | 5 new distribution channels activated; sales team trained (95% completion)
PHASE 4: PERFORMANCE MONITORING & OPTIMIZATION
Phase 4A | Implement KPI Dashboards and Reporting System | Develop real-time analytics, automate reporting tools | Data & Insights Team | 2024-01-16 | 2024-01-31 | Not Started | Dashboards live and accessible to leadership team by Q1 end
Phase 4B | Milestone Review & Iterative Refinement | Monthly review meetings, feedback integration, plan adjustments | Project Steering Committee | Ongoing (monthly) | Ongoing (until project close) | In Progress | Action items from reviews tracked and resolved within 48 hours
TOTAL PROJECT SUMMARY | [6 empty] | Projected Q1 Growth: +22% YoY