## Growth Planning - Project Plan
Growth Planning - Project Plan
Phase | Activity/Task | Responsible Team | Start Date | End Date | Status | Budget (USD)
Initiation & Planning Phase
1.1 | Define Growth Objectives and KPIs | Strategy Team | 2024-04-01 | 2024-04-15 | In Progress | $5,000
1.2 | Market Research & Competitive Analysis | Market Research Team | 2024-04-16 | 2024-05-15 | Pending | $8,500
Execution & Development Phase
2.1 | Develop Growth Strategy Framework | Strategy & Product Team | 2024-05-16 | 2024-06-30 | Pending | $15,000
2.2 | Design Customer Acquisition Campaigns | Marketing Team | 2024-06-01 | 2024-07-31 | Pending | $18,000
Monitoring & Evaluation Phase
3.1 | Launch Pilot Programs (Phase 1) | Operations & Marketing | 2024-08-01 | 2024-09-30 | Pending | $12,500
3.2 | Track KPIs & Performance Metrics | Data Analytics Team | 2024-08-15 | 2024-11-30 | Pending | $7,500
Final Review & Reporting Phase
4.1 | Compile Growth Report & Insights | Strategy Team | 2024-10-01 | 2024-11-30 | Pending | $6,500
Total Project Budget: | [5 empty] | $73,000