## Worksheet
Phase/Task | Start Date | End Date | Status | Owner | Budget (USD) | Milestones
Initiation & Planning | 2023-10-01 | 2023-10-15 | In Progress | Jane Doe - Project Manager | $5,000 | Project Charter Signed, Stakeholders Confirmed
Market Research & Analysis | 2023-10-16 | 2023-11-30 | To Do | Mark Lee - Analyst | $8,500 | Competitor Analysis Complete, Customer Survey Results Compiled
Strategy Development | 2023-12-01 | 2023-12-31 | To Do | Sarah Kim - Strategy Lead | $7,000 | Go-to-Market Plan Finalized, KPI Framework Set
Product Roadmap Planning | 2024-01-01 | 2024-01-31 | To Do | Alex Johnson - Product Owner | $6,500 | Roadmap Approved by Stakeholders, Feature Prioritization Complete
Resource Allocation & Hiring | 2024-02-01 | 2024-03-15 | To Do | Lisa Chen - HR Manager | $15,000 | Key Roles Filled, Onboarding Completed
Development & Implementation (Phase 1) | 2024-03-16 | 2024-05-31 | To Do | Mike Rodriguez - Tech Lead | $45,000 | Core Features Built & Tested, MVP Ready for Pilot Launch
Pilot Launch & Feedback Collection | 2024-06-01 | 2024-07-15 | To Do | Emma Wilson - UX Lead | $8,000 | Pilot Successful, Feedback Report Delivered, Improvements Identified
Full Rollout Preparation | 2024-07-16 | 2024-08-31 | To Do | Taylor Brown - Operations Manager | $10,500 | Training Materials Ready, Infrastructure Scaling Complete
Full Market Launch | 2024-09-01 | 2024-11-30 | To Do | Daniel Green - Marketing Director | $65,000 | Landing Page Live, Campaigns Active, First 5K Users Acquired
Total Budget (Estimated) | [5 empty] | $170,500
Note:This project plan is for client view only and subject to change based on business needs and feedback.