## Worksheet
Phase | Key Objective | Start Date | End Date | Status | Owner
Growth Strategy Development | Define core growth targets and KPIs for next fiscal year. | 2024-01-01 | 2024-01-31 | In Progress | Alice Johnson
Market Research & Analysis | Collect and analyze data on target markets and customer behavior. | 2024-02-01 | 2024-03-15 | Pending | Brian Lee
Product Enhancement Planning | Create roadmap for product features aligned with growth goals. | 2024-03-16 | 2024-04-30 | Pending | Chris White
Marketing Campaign Design | Develop go-to-market strategy and campaign assets. | 2024-05-01 | 2024-06-15 | Pending | Dana Patel
Team Scaling & Hiring | Identify and onboard new talent to support expansion. | 2024-06-16 | 2024-08-31 | Pending | Evan Moore
Metric Tracking Implementation | Leverage analytics tools to monitor progress in real time. | 2024-09-01 | 2024-10-31 | Pending | Fiona King
Quarterly Review & Adjustment | Evaluate results and refine strategy for next cycle. | 2024-11-01 | 2024-11-30 | Pending | Alice Johnson