## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assignee | Status | Progress (%) | Dependencies | Priority
TP-001 | Define Growth Objectives | 2024-01-05 | 2024-01-15 | 11 | Jane Doe | In Progress | 75 | N/A | High
TP-002 | Market Research & Analysis | 2024-01-16 | 2024-01-31 | 16 | John Smith | In Progress | 50 | TP-001 | High
TP-003 | Create Target Customer Profiles | 2024-02-01 | 2024-02-15 | 15 | Sarah Lee | Not Started | 0 | TP-002 | Medium
TP-004 | Develop Growth Strategy Framework | 2024-02-16 | 2024-03-15 | 30 | Liam Brown | Not Started | 0 | TP-003, TP-015 | High
TP-005 | Identify Key Growth Channels | 2024-03-16 | 2024-03-31 | 16 | Mia Johnson | Not Started | 0 | TP-004, TP-016 | High
TP-006 | Create Marketing Campaign Plan | 2024-04-01 | 2024-04-30 | 30 | Ava Martinez | Not Started | 0 | TP-015, TP-017, TP-021 | Medium
TP-007 | Develop Product Roadmap for Growth | 2024-04-15 | 2024-05-31 | 46 | Noah Wilson | Not Started | 0 | TP-019, TP-023 | High
TP-008 | Budget Allocation & Forecasting | 2024-05-15 | 2024-06-15 | 31 | Ella Davis | Not Started | 0 | TP-018, TP-024, TP-027 | High
TP-009 | Pilot Launch Phase 1 (Beta) | 2024-06-16 | 2024-07-31 | 46 | Lucas Taylor | Not Started | 0 | TP-025, TP-031, TP-034, TP-042 | High
TP-010 | Analyze Pilot Results & Adjust Strategy | 2024-08-01 | 2024-08-31 | 31 | Aria White | Not Started | 0 | TP-035, TP-047, TP-052, TP-061 | High
Total Tasks: 10 ¦ Completed: 2 ¦ In Progress: 2 ¦ Not Started: 6