## Worksheet
GROWTH PLANNING - EXTENDED PROJECT PLAN
Phase | Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
PHASE 1: STRATEGY & RESEARCH
1.1 | TASK-001 | Market Opportunity Analysis | Marketing Director | 2023-10-01 | 2023-10-15 | In Progress | 75%
1.2 | TASK-002 | Competitor Benchmarking Report | Business Analyst | 2023-10-16 | 2023-11-05 | Pending | 0%
PHASE 2: PLANNING & DESIGN
2.1 | TASK-003 | Product Roadmap Development | Product Manager | 2023-11-06 | 2023-11-30 | In Progress | 50%
MILESTONE 1: STRATEGY APPROVAL (Nov 30, 2023)
PHASE 3: EXECUTION & LAUNCH
3.1 | TASK-004 | Development Sprint Planning (Q1) | Engineering Lead | 2023-12-01 | 2023-12-15 | Pending | 0%
MILESTONE 2: Q1 PRODUCT LAUNCH (Dec 31, 2023)
PHASE 4: SCALING & OPTIMIZATION
4.1 | TASK-005 | Growth Metrics Dashboard Setup | Analytics Team | 2024-01-01 | 2024-01-15 | Pending | 5%
MILESTONE 3: QUARTERLY GROWTH REVIEW (Jan 31, 2024)