## Worksheet
Growth Planning - Large Business Project Plan
Template Type: Project Plan ¦ Purpose: Growth Planning ¦ Version: Large Business
# | Task ID | Task Description | Start Date | End Date | Duration (days) | Owner | Status | Progress
Growth Strategy Initiative - Q3-Q4 2024
1 | GS-001 | Milestone: Market Research & Analysis Complete | 2024-07-01 | 2024-07-31 | 31 | Jane Doe | Completed
2 | GS-002 | Milestone: Product Expansion Plan Finalized | 2024-08-15 | 2024-09-30 | 46 | Mark Lee | In Progress
3 | GS-003 | Milestone: New Market Entry Strategy Approved | 2024-10-15 | 2024-11-30 | 46 | Sarah Chen | Delayed
4 | GS-101 | Conduct competitive analysis across key regions | 2024-07-01 | 2024-07-15 | 15 | Jane Doe | Completed
5 | GS-102 | Identify high-growth customer segments | 2024-07-16 | 2024-07-31 | 16 | Jane Doe | Completed
6 | GS-201 | Develop prototype for new product line A | 2024-08-15 | 2024-09-30 | 46 | Mark Lee | In Progress
7 | GS-202 | Test prototype with pilot customers | 2024-10-01 | 2024-10-31 | 31 | Lisa Park | Delayed
8 | GS-301 | Finalize regulatory compliance documentation for EU market | 2024-10-15 | 2024-11-30 | 46 | Sarah Chen | Delayed
Total Tasks: | [6 empty] | 8
Project Plan Version 1.0 ¦ Created on July 1, 2024 ¦ For Internal Use Only